## Sheet1
SCREEN | START DATE | END DATE | DEVELOPER NAME | UI ISSUES | DAYS | % COMPLETE
Completed
Login | [5 empty] | 100
hr/ manager Employee Tracker | 2017-09-14 | 2017-09-15 | Ajith | react table error | 2 | 100
leave management (pending approval, leave list) | 2017-09-18 | 2017-09-21 | Ajith |  | 4 | 100
Employee page | 2017-09-22 | 2017-09-25 | Ajith |  | 2 | 100
Balance
Dashboard |  |  | Ajith | under planning,
Employee tracker (leave approval) |  |  | Ajith
leave management (leave application, leave history) |  |  | Ajith
project |  |  | Ajith
Time sheet |  |  | Ajith
Mockups
Employee tracker - employee details, project details)
Project - (project detail)
Time sheet - (HR/Manager view)
Payslip
Payroll
Report